## Backlog
Product Backlog
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
1 | Class-diagram |  | M | x
2 | Start menu |  | M |  | x
3 | A Start button |  | M |  | x
4 | A quit button |  | M |  | x
5 | Score button |  | M |  | x
6 | rules Button |  | M |  | x
7 | A moveable character |  | M |  | x
8 | Random Object spawn |  | M |  |  | x
9 | a Winning method |  | M |  |  | x
10 | A losing method |  | M |  |  | x
11 | End game screen |  | M |  |  | x
12 | Cross-plateform |  | M |  |  | x
13 | Bonus |  | C |  |  | x
14 | DataBase |  | S |  |  | x

## Sprint 1
Sprint 1 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As I developer I want to know how the will be developed through class- diagram because the development porcess will go better | M | 2h | make a class-diagram ad build as you go through the sprints | It explains the interactions in the game

## Sprint 2
Sprint 1 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
2 | As an user I must be able to have a start screen so that I can access all the features | M | 2h | 1. a screen that lunches at the begening. 2. It has 4 buttons | The player as he launches the game gets a screen acts as main menu with 4 options that can be used to navigate
3 | As an user I must be able to start a match so that I can play | M | 2.5h | 1. make a start button 2. The button is located on the start screen 3. it leads you to the game page | The player can start the game with the start button and he goes to the page where he can play
4 | As an user I must be able to quit the game because I need to stop when I need to | M | 2h | 1. make a quit stop button 2. The button is located on the I screen 3. It closes the game | The player can click on the quit button to exit the game
5 | As an user I must be able to review the score so that check my highscore | M | 2h | 1. make a score button 2. The button is located on the review screen 5. it leads you to the score page | The player can check the score of players through clicking on the score button
6 | As an user I must be able to read the rules of the game so that I can understand the game | M | 2.6h | 1. make a rules that button 2. The button is located on the game screen 3. it leads you to the rules page | The player can read the rules through clciking the rules button
7 | As an user I want to controle the character so that I can play | M | 5h | 1. make a character 2. make it moveable 3.The player can controle it | The player can fully controle the character and the character as the game starts

## Sprint 3
Sprint 1 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria