## Blad1
Projectnaam | User story # | Work item # | 26-07 - Remaining Hours | 27-07 Remaining Hours | 28-07 Remaining Hours | 29-07 Remaining Hours
Sprint 2 | User story 4 | Work item 4 | 1 | 1 | 1 | 0
| User story 5 | Work item 5 | 4 | 3 | 2 | 0
| User story 6 | Work item 6 | 1 | 1 | 1 | 0
| User story 7 | Work item 7 | 2 | 1 | 1 | 0
|  | Ideal | 8 | 5.33 | 2.66 | 0
|  | Actual | 8 | 6 | 5 | 0