## Backlog
Product Backlog
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
1 | Class diagram |  | M | x
2 | Main menu |  | M |  | x
3 | Start button |  | M |  | x
4 | Quit button |  | M |  | x
5 | Score button |  | M |  | x
6 | Rules Button |  | M |  | x
7 | A moveable character |  | M |  | x
8 | Random apples spawning |  | M |  |  | x
9 | Winning method |  | M |  |  | x
10 | Losing method |  | M |  |  | x
11 | End game screen |  | M |  |  | x
12 | Cross platform |  | M |  |  | x
13 | Bonus / buffs |  | C |  |  | x
14 | Database |  | S |  |  | x

## Sprint 1
Sprint 1 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a developer I want to know how the game will be developed through a class diagram so that I know what to code. | M | 2h | 1. Find out what to code for a snake game 2. Make a class diagram | All parts for the snake game code is in the diagram.

## Sprint 2
Sprint 1 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As an user I must be able to have a start screen so that I can access all the features. | M | 2h | 1. A screen that launches at the beginning. 2. It has 4 buttons. | The player gets a screen that acts as main menu with 4 options that can be used to navigate as he launches the game.
2 | As an user I must be able to start a match so that I can play. | M | 2.5h | 1. Make a start button. 2. The button is located on the start screen. 3. It leads you to the game page. | The player can start the game with the start button. The screen where the player gets to play the game will appear.
3 | As an user I must be able to quit the game when I want. | M | 2h | 1. Make a quit/stop button. 2. The button is located on the I screen. Inside the setting menu. 3. It closes the game. | The player can click on the quit button to exit the game. The game will get back to the main menu. On the main menu screen there is another Quit button which will shut down the game.
4 | As an user I must be able to check my score while playing and review the score so that check my highscore. | M | 2h | 1. Make a high score button. 2. The button is located on the main menu screen. 3. A database might be needed. 4. Get a score counter in the game. | The player can check the score of players through clicking on the score button
5 | As an user I must be able to read the rules of the game so that I can understand the game. | M | 2.6h | 1. Make a game rules button. 2. The button is located on the main menu screen and inside the settings screen when the game is on going. 3. It leads you to the rules page. | The player can read the rules. The buttons are located and working accordingly.
6 | As an user I want to control the character so that I can play. | M | 5h | 1. Make a character (snake) 2. Make it moveable 3. The player can control it | The player can fully control the character as the game starts.

## Sprint 3
Sprint 1 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria