## Backlog
Product Backlog
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
1 | Screens: Main menu, In-Game screen, Settings / Rules screen, End game screen and High score screen. Buttons: Start game, Settings, High score, Quit game |  | M |  | x
2 | Create settings menu inside the Settings Menu with difficulty modes, sound settings and rules in it |  | M |  | x
3 | A score counter in the game. High score ranking system. |  | M |  | x
4 | Write the rules |  | M |  | x
5 | Create moveable Snake character with head and tail that grows when eating apples |  | M |  | x
6 | Playing field/map with borders |  | M |  | x
7 | Random apples spawning |  | M |  | x
8 | Windows / PC and android compatible |  | M |  | x
9 | Bonus / buffs |  | S |  |  | x
10 | Add sound / BGM |  | S |  |  | x
11 | Add images / title image |  | S |  |  | x

## Sprint 1
Sprint 1 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria

## Sprint 2
Sprint 2 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria
1 | As a user I want a main menu that starts at the start of the program. In the main menu there are buttons that I can use to navigate through the program: Start game, Settings and Rules screen, High Score screen and quit game. | M | 0.5h | 1. A screen that launches at the beginning. 2. It has a big title of the game Snake and 4 buttons: Start Game; Settings; High Score; Quit Game 3. The 3 buttons lead to the other screens. Quit Game ends the program. | The player gets a screen that acts as main menu with 4 options that can be used to navigate as he launches the game.
2 | As a user I want to change the difficulty of the game and to turn sound on or off and adjust other settings. | M | 0.5h | 1. Make a Settings screen. 2. The Settings button is located on the main enu screen and also in the right side of the in-game Snake screen. The settings screen must also be accesible with a key input while playing. 3. It leads you to the Settings screen. 4. In the Settings screen the user is able to turn sound on or off and read the rules. 5. With the Back button the user will be brought back to the main menu or the in-game screen if the user is playing. | The player is able to access the Settings screen. The player can adjust settings in the Settings screen and read the rules.
3 | As a user I must be able to check my score while playing and review the score afterwards so that I can check my highscore. | M | 1h | 1. Make a high score button. 2. The button is located on the main menu screen. 3. A database or something else to save data might be needed. 4. Get a score counter in the game. | The player can check the score of players through clicking on the score button. The buttons are located and working accordingly.
4 | As a user I must be able to read the rules of the game so that I can understand the game. | M | 1h | 1. Make a game rules button. 2. The button is located on the main menu screen and inside the settings screen when the game is on going. 3. It leads you to the rules page. | The player can read the rules. The buttons are located and working accordingly.
5 | As a user I want to control the snake character in the playing map so that I can play the game. The Snake must grow larger each time it eats an apple to make the game difficult the longer you play. If the snake moves to itself, the game will be over. | M | 4h | 1. Make a character (snake) 2. Make it moveable and the player can control it 3. Write the code: The snake has a head and a tail. The tail follows the head. 4. Write code: The snake grows when it eats an apple. 5. Implement in the code that the game will be over if the snake moves in itself. | The player can fully control the character as the game starts. The head and tail of the snake acts accordingly.
6 | As a user I need a map to play the Snake game on. The map should have borders: if the snake moves into a border, the game is over. | M | 1h | 1. Create a draw class that draws the map. 2. Give the map borders. 3. Implement in the code that if the snake moves into the border, the game will be over | There is a map when the game starts. The Snake starts in the center of the map. There are borders on the map. Everyyhing works correctly as written in the Tasks.
7 | As a user I want to collect the apples so that I can get a higher score | M | 2h | 1. Write a code that spawns apples randomly in the map. 2. Write a code that if Snake eats an apple, the score will increase and the snake will grow. | Apples spawn in a random place inside the map. The Snake will grow and the scroe increases when the snake eats an apple.
8 | As a user I want to play the game on my computer as well as on my phone. | M | 2h | 1. First make the game android compatible. 2. Make the game screen bigger to fit the size of the computer screen 3. Make the program Windows compatible. | The game is playable on phone and computer and fully working and correctly.

## Sprint 3
Sprint 3 Backlog
ID | User story | Priority | Time estimation | Tasks | Acceptance criteria