## Blad1
Projectnaam | User story # | Work item # | 19-07 - Remaining Hours | 20-07 Remaining Hours | 21-07 Remaining Hours | 22-07 Remaining Hours
Sprint 1 | User story 1 | Work item 1 | 3 | 2 | 2 | 0
|  | Ideal | 3 | 2 | 1 | 0
|  | Actual | 3 | 2 | 2 | 0